## Sheet1
Change Request Form - BI Dashboard Project
Change Request ID# | SW-BI-112905622
Requested by | Marcella Davidson - BI Development Team Lead
Date of Request | 2017-12-04
Current BI Report Capabilities | The dashboard for electricity consumption by the government displaced program is aimed at presenting on-line electricity usage by the tenants of the new housing project in the province of Guadalupe, North Huaraz, Colombia
Reason for the Request | Currently the dashboard can only present the electrical usage of a given unit (apartment) for the previous 24 hours, and cannot break the usage down into hours. This will prevent the authorities from being able to predict usage spikes, and produce auxiliary electricity for those spikes timeframes
Expected BI Report Capabilities Post Change | The dashboard will present the hourly electricity usage (in Kilo Watts) for every hour in the past 24 hours, per every unit in the housing project. It will also be able to present an aggregate view of the past 24 hours, per every hour
Impact of Change | The new capabilities will require an extra 37 hours of development, and 6 more QA hours. These hours will cost an additional $3,145 for the development (37 X $85) and $360 for the QA (6 X $60). All in all the new capabilities will cost an additional $3,505. The timeline will be delayed by 2 weeks, which is in the buffer of the project (3 buffer weeks remain)
Received by | Shirley Thorpe - Lead SW Project Manager
Status of CR | Approved
Date of CR status change | 2017-12-06