## Summary
Issues Summary
Total Open Issues | 1
Total New Issues | 2
Total Issue On-Hold | 1
Total Unresolved Issues | 4
Total Issues with Severity "Critical" | 1
Total Issues with Priority "Urgent" | 1
Total Issues marked "High" | 3

## Issue Register
No. | Issue Title | Issue Description | Reported On | Reported By | Owner | Severity | Priority | Status | Comments
1 | Code Module Issue | An issue with code module was recently idenfitied. The user is not able to make changes to the rates. | 2015-02-25 | Neel | Julie | Low | High | New | SRW 07-Feb : New Issue logged today.
2 | User Access Issue | Some of the users are not able to login. | 2015-03-23 | Swapnil | Kamel | High | Urgent | WIP | SRW 25-Mar : Issue is affecting service levels.
3 | Server Memory Issue | One of the server mmx0013 has memory issues and needs to be looked at. This memory issue is causing a performance issue with the application. | 2015-03-26 | Jack | Cathy | Medium | High | Closed
4 | User Interface Issue | Users are not able to make changes to certain fields when updating. | 2015-04-01 | Sam | Julie | Low | Medium | OnHold | SRW 05-Apr : On Hold due to business confirmation.
5 | Spelling Error | One of the fields has a spelling error. | 2015-04-02 | Neel | Jim | Critical | Low | New | SRW 04-Apr : New Issue.

## Lists
Severity | Priority | Status
Critical | Urgent | New
High | High | WIP
Medium | Medium | Closed
Low | Low | OnHold