## Project Estimation
Project Estimation Template
Project Name | Software development project |  |  | Project Id | PR18379
Project Manager | Tim Jones |  |  | Project Sponsor | Danny Hobson
Start Date | 2018-02-01 |  |  | End date | 2019-04-30
Project Deliverable | Estimated hours | Resources | Cost (000s) | Remarks
Initiation/Planning
Feasibility Study | 5 | 1 | 2.5
Business case | 5 | 1 | 10
Project Charter | 3 | 1 | 10 | Project manager
Project planning | 32 | 2 | 25
Requirement Analysis
Requirements gathering | 16 | 2 | 50 | Business Analyst
Design
High Level design | 10 | 2 | 50
Detailed design | 16 | 2 | 75
Technical specificaiton | 24 | 3 | 20
Development
Build/Develop | 80 | 4 | 100 | Developers
Documentation | 10 | 1 | 10 | Project manager
Test planning | 6 | 1 | 10 | Testers
Deployment planning | 10 | 3 | 15
Training planning | 7 | 2 | 20
Transition planning | 6 | 2 | 9
QA
Unit test | 9 | 2 | 4.5
Funciton test | 12 | 2 | 8
Integration test | 12 | 2 | 8
Regression test | 12 | 1 | 5
System test | 8 | 1 | 12
User acceptance test | 18 | 4 | 25
Implementation
Deployment | 10 | 4 | 50
Training | 10 | 2 | 60
Support | 15 | 2 | 40
Operations & Maintenance
Operations activities | 10 | 1 | 20
Maintenance activities | 8 | 1 | 19
Estimated Total Cost | 658
Estimated Total Resources | 48
Estimated Total Time | 354 | 14.75 days