## Release
Feature Name | Sprint | Start Date | End Date | Status | Goal
Sprint #0 - Release Planning
Allow the user to export their personal information into an Excel sheet | Sprint #2 | 2017-11-30 | 2017-12-05 | Assigned | Allowing the users to export their data into an Excel sheet will allow them to better "Slice & Dice" the info into useful information
Add customization features to the chart area (Font size, Colours, Chart type, etc.) | Sprint #1 | 2017-12-05 | 2017-12-12 | Initialized | Easily done, and highly appreciated by the users
Add a password remembrance feature, allowing users to save their p/w for easier access | Sprint #2 | 2017-12-04 | 2017-12-08 | Planned | Add the interface to the browser listing
Streaming capabilities | Unplanned | N/A | N/A | Planned | Allow the users to stream live info to their devices
Tagging pictures / images | Sprint #1 | 2017-12-11 | 2017-12-14 | Initialized | Allow the users to tag any image they upload
On-Line updates from external sites | Sprint #3 | 2017-12-11 | 2017-12-14 | Assigned | Collect data from other sites, and present to the users with a 20 minute lag
Pop-up advertisements according to the users location | Sprint #4 | 2017-12-18 | 2017-12-22 | Planned | Requires an interface to the GPS or location data of the users